## Plan
Group11 - AI Patient FollowUp Assistant | [5 empty] | 2026
# | Task | Owner | PED/Sprint/week | Status | Deliverable Required | Remark
1 | High Level Design and architecture documentation | Rohith | Week1 [25 May - 31 May] | Closed
2 | Plan Preparation | All | Week1 [25 May - 31 May] | Closed
3 | Synthetic data preparation | Manisha/Reffel | Week2 [1 June - 7 June]
4 | RAG setup | Rohith | Week2 [1 June - 7 June]
5 | Agent Workflow plannig/design | Reffel | Week2 [1 June - 7 June]
6 | Summary Agent Implementation |  | Week3[8 June - 14 June] |  | Yes | SourceCode
7 | Reminder Agent Implementation |  | Week3[8 June - 14 June] |  | Yes | SourceCode
8 | Escalation Agent Implementation |  | Week3[8 June - 14 June] |  | Yes | SourceCode
9 | Workflow Integration |  | Week3[8 June - 14 June] |  | Yes | SourceCode
10 | FrontEnd Implementation[Steamlit] | Pradeep | Week3[8 June - 14 June] |  | Yes | SourceCode
11 | AWS Deployment | Pradeep | Week4[15 June - 25 June] |  | Yes | AWS Deployment proof(EC2 and S3)
12 | Testing |  | Week4[15 June - 25 June]
13 | Final Report | Manisha | Week4[15 June - 25 June] |  | Yes | A word document
14 | Final PPT Report | Manisha | Week4[15 June - 25 June] |  | Yes | PPT document
15 | Presentation Recording |  | Week4[15 June - 25 June] |  | Yes